## Sheet1
K&S Building Management Services Report
Date: | 24.10.2013 |  |  | SP 69259 Mondrian Apartments
Status | Item | Contractor/Worker | Current Situation | Action taken or Required | Time Required |  | Resolution
Open | Energy | City Of Sydney Council & John Hutchison | Energy price increases from July 1 2012 | Mondrian Apartments to participate in Smart Green Apartments Program to look at possible ways to be more energy efficient and reduce energy consumption. | On-going |  | TBA
Open | Common area lighting | K&S BMS | Common Area Lighting.Upgrade of existing halogen down lights to LED(20 watt) | LED lighting received for stage 2 upgrade of existing halogen down lights to LED in common areas. Continuing to replace existing halogens with LED as they fail. Including all lift lights as they fail. | On-going | on-going | TBA
Open | Pool Lights | K&S BMS | 4 lights working and one is out | Cannot find current fittings.Have taken measurements/size of pool light hole and await quotes for replacement. | On-going | on-going | TBA
Open | George Fischer pipes | K&S BMS & MRC Plumbing | Whilst performing daily inspections, 4.09.2013, I found that a hot water pipe just outside lot 30 in car park was leaking | Engaged MRC Plumbing to clamp the pipe. Repaired 10.9.2013 | Completed |  | TBA
Open | Cleaning | K&S BMS | Quality of cleaning continues to be monitored closely by BM. | BM continuing to work closely with cleaning staff and undertaking daily inspections. | On-going |  | TBA
Open | Car park,Fire stairs & emergency lights | K&S BMS | Lights in these areas are on 24 hours per day, 7 days per week | Have engaged Megger to supply a quote to upgrade all these areas with more energy efficient alternatives. | on-going |  | TBA
Open | Boiler Room | K&S BMS & CBD Plumbing | Performing daily inspections, I found in the boiler room hot water leaking from the TMV assembly | Engaged CBD Plumbing to repair. They removed faulty washers and replaced with teflon gromets. Received a quote from CBD Plumbing with 2 alternatives. Have asked MRC for a 2nd quote | TMVs are pre 2008 and parts are no longer available. It is recommended to replace all 7 TMV and Ball valves |  | TBA
Open | Plumbing - 208 | K&S BMS & CBD Plumbing | 4.09.2013 informed of possible burst pipe in bathroom. Water was pooling in living area as water was coming from behind the wall which housed the bathroom. | Engaged CBD Plumbing to repair.Cut hole from back of wall in dining area and repaired split breech. Re-assembled & water proofed. Handyman engaged and began work 21.10.2013 | 4.11.2013 will see completion
Open | Pets | K&S BMS | Recently informed of dogs in the complex without approval from EC/Strata. 354 and 227 | Strata have been notified for action | On-going |  | TBA
Open | MYBOS | K&S BMS | New Building Management/Community portal system requires population | Have a meeting with Sam next week to clarify a few issues. | On-going |  | TBA
Open | Fire alarm activated | K&S BMS | 4.09.2013 a new tenant drove an oversized truck into the car park. On departing has knocked off a fire sprinkler head setting off alarms and causing havoc with residents as no-one came in or out for over half an hour. Tenant 320 | Liaised with Fire Department as they repaired broken fire sprinkler head. Informed EC/Strata of the incident and Liberty R/E immediately. Manually opened up roller doors to allow entry for owners/residents once sprinkler head repaired. | Still waiting on an Invoice from RFS |  | TBA
Open | Water pump in Plant room next to Powell St lawn | K&S BMS & Kelair | Whilst inspecting the property I noticed a water pump fault in the plant room 11.10.2013 | Have engaged Kelair and advised Strata/EC of this fault. Work order placed and await Kelair on-site | On-going |  | TBA
Open | Plumbing/bathroom tile repair 354 | K&S BMS | 354 recently had a pipe burst in the bathroom wall. Hole in bathroom to be repaired/waterproofed and re-tiled | Engaged Handy-Fix Solutions. Work began 13.09.2013 to repair wall and water proof. 20.09.2013 saw tile replacement and completion | Completed 20.09.2013 |  | TBA
Open | Apartment 225 water ingress from 2nd bedroom window | K&S BMS & Magellan | 2nd bedroom window continues to have water ingress | After siliconing and repairing the latch on the window, Magellan were engaged to install an aluminium weather protection shield. | Completed 16.10.2013
Open | Lighting B1 common area | K&S BMS & Meggers Electrical | I have found that circuit 35 in B1 keeps tripping therefore disabling the garden lights | Megger engaged to rectify as this was recently repaired. Due to the rain early this week this will be re-visited again 19.09.2013. | Completed |  | TBA
Open | Bicycle cages | K&S BMS | Bicycle cages require an update of the log | Letters/notices placed on cages requesting notification of use.Update current file of current and new users. Also ordered 2x keys to every lock | On-going |  | TBA
Open | By-Law Breaches | K&S BMS | 201208223401 | Breach notifications issued to tenants. Strata & EC informed | On-going |  | TBA
Open | Roofing | K&S BMS | Barge capping and roof are blowing off and require repair/maintenance | Have had 2x emergencies in the last 3 months where barge capping and the roof have almost blown off in the winds. Have received 1 quote from Sydney roofers and had another roofer on-site 22.10.2013 to compile a second quote. | On-going |  | TBA
Open | Access panels | K&S BMS, AE&D & IBC | For compliance Fire Inspection access panels need to be installed in all apartments | Have liased with AE&D. Notified tenants/owners/Real Estate Agents and made myself available for those residents and owners who could not grant access on the day to the trademen. | On-going |  | TBA
Open | Security audit | K&S BMS | Security audit required | Security audit will proceed from 1.11.2013 til 14.12.2013 | On-going |  | TBA
Open | Building 2 & 4 Glass doors | K&S BMS & Obriens | B2 and B4 glass entry doors not closing as expected | Engaged Obriens Glass 11.10.2013 to service doors and replace spindles | Completed 15.10.2013
Open | Graffiti | K&S BMS | 19.10.2013 Saturday evening/Sunday morning Southern fire stairs outside 323 graffitied | Engaged a painter 22.10.2013. Found the correct colour and will complete work 24.10.2013. CCTV is blind in that area and could not detect anything suspicious between 2000-0630 the next day. | Painting was completed 24.10.2013
Open | Common area pavers | K&S BMS | Some common area pavers are becoming uneven and pose as a tripping hazard | Have inspected and found that roots under some pavers are dislodging in some areas and making for uneven surfaces around the complex. Have engaged 3 tilers for a quote to investigate to repair. | On-going |  | TBA