## Sheet1
K&S Building Management Services Report
Date: | 2013-09-18 |  |  | SP 69259 Mondrian Apartments
Status | Item | Contractor/Worker | Current Situation | Action taken or Required | Time Required |  | Resolution
Open | Energy | City Of Sydney Council & John Hutchison | Energy price increases from July 1 2012 | Mondrian Apartments to participate in Smart Green Apartments Program to look at possible ways to be more energy efficient and reduce energy consumption. | On-going |  | TBA
Open | Common area lighting | K&S BMS | Common Area Lighting.Upgrade of existing halogen down lights to LED(20 watt) | LED lighting received for stage 2 upgrade of existing halogen down lights to LED in common areas. Continuing to replace existing halogens with LED as they fail. Including all lift lights as they fail. | On-going | on-going | TBA
Open | Pool Light | K&S BMS | One pool light has blown the 12V driver and is currently not working | Investigated and engaged Megger to rectify. Megger and I identified the faulty light and found that this has shorted out the previous driver. Driver replaced however still sourcing a light as they are not found in Australia. | On-going | on-going | TBA
Open | George Fischer pipes | K&S BMS & MRC Plumbing | Whilst performing daily inspections, 4.09.2013, I found that a hot water pipe just outside lot 30 in car park was leaking | Engaged MRC Plumbing to clamp the pipe and await acceptance of a quote to repair | On-going |  | TBA
Open | Cleaning | K&S BMS | Quality of cleaning continues to be monitored closely by BM. | BM continuing to work closely with cleaning staff and undertaking daily inspections. Will also be having a walk-thru on 19.09.2013 with 2x EC members | On-going |  | TBA
Open | Defects | Paul Evans, Suzy Broome, St Hilliers. Allianz | Ongoing building defect issues and additional items. Report finalised. | Awaiting on confirmation from Sergon regarding the commencement date for the defect repairs | on-going |  | TBA
Open | Boiler Room | K&S BMS & CBD Plumbing | Performing daily inspections, I found in the boiler room hot water leaking from the TMV assembly | Engaged CBD Plumbing to repair. They removed faulty washers and replaced with teflon gromets. | TMVs are pre 2008 and parts are no longer available. It is recommended to replace all 7 TMV and Ball valves |  | TBA
Open | Plumbing - 208 | K&S BMS & CBD Plumbing | 4.09.2013 informed of possible burst pipe in bathroom. Water was pooling in living area as water was coming from behind the wall which housed the bathroom. | Engaged CBD Plumbing to repair.Cut hole from back of wall in dining area and repaired split breech. Re-assembled & water proofed. Handyman has been engaged to repair hole(gyprock wall) depending on owner for access | On-going |  | TBA
Open | Pets | K&S BMS | Recently informed of dogs in the complex without approval from EC/Strata. 336,354 and 227 | I have informed Strata and have requested an answer from Liberty R/E regarding 336. | On-going |  | TBA
Open | MYBOS | K&S BMS | New Building Management/Community portal system requires population | Currently, owner/occupiers and contractors have been populated. One present glitch is that it will not accept owners and residents. Just the 1 category. | On-going |  | TBA
Open | Fire alarm activated | K&S BMS | 4.09.2013 a new tenant drove an oversized truck into the car park. On departing has knocked off a fire sprinkler head setting off alarms and causing havoc with residents as no-one came in or out for over half an hour. Tenant 320 | Liaised with Fire Department as they repaired broken fire sprinkler head. Informed EC/Strata of the incident and Liberty R/E immediately. Manually opened up roller doors to allow entry for owners/residents once sprinkler head repaired. | Completed 4.09.2013
Open | Residents of 320 & pets | K&S BMS & Liberty R/E | Informed that 320 had recently moved in with 2x small dogs | Emailed Liberty R/E and Strata requesting dog applications for 320. Liberty R/E were disappointed in the new tenants and their willingness to attempt to hide this in their application especially after the incident on 4.09.2013. Tenancy agreement subsequently terminated. | Completed
Open | Plumbing/bathroom tile repair 354 | K&S BMS | 354 recently had a pipe burst in the bathroom wall. Hole in bathroom to be repaired/waterproofed and re-tiled | Engaged Handy-Fix Solutions. Work began 13.09.2013 to repair wall and water proof. 20.09.2013 will see tile replacement | On-going |  | TBA
Open | Apartment 225 water ingress, faulty smoke detector | K&S BMS | Wired smoke detector hanging from roof and water ingress issues from bedroom window seal fault | Inspected 3.08.2013 and found that smoke detector requires urgent repair. Repaired 13.08.2013. Heavy water ingress through the window of 2nd bedroom. Have engaged Handy-fix solutions to repair 20.09.2013 | On-going |  | TBA
Open | Lighting B1 common area | K&S BMS & Meggers Electrical | I have found that circuit 35 in B1 keeps tripping therefore disabling the garden lights | Megger engaged to rectify as this was recently repaired. Due to the rain early this week this will be re-visited again 19.09.2013. | On-going |  | TBA
Open | Bicycle cages | K&S BMS | Bicycle cages require an update of the log | Letters/notices placed on cages requesting notification of use.Update current file of current and new users. Also ordered 2x keys to every lock | On-going |  | TBA
Open | By-Law Breaches | K&S BMS | 208 - Mirror ball in courtyard. 201 - lot cleanliness | 208 has been served with 2 x breach notices requesting the removal of the mirror ball. 201 recently breached for the lack of cleanliness of the courtyard | Work completed |  | TBA
Open | Intercom issues | K&S BMS & NTS | 30.08.2013 informed of intercom for 309-312 was faulty. | Investigated and found that intercom was not responsive. Engaged NTS to repair.2.09.2013 NTS were on-site when suspected power surge has left 2 more intercoms useless. 3x control panels required to be replaced. That is 309-312 intercom, Intercom between B1 & B2 and the intercom leading into the car park. | Work completed 22.07.2013 |  | TBA
Open | Water ingress to Apt 117 | K&S BMS & Biltbeta | Water ingress into main bedroom | I have inspected and taken photographs. Taylors were given roof access 1.08.2013 to determine point of water ingress. Will quote to water test. Advised to record/include and liaise with Biltbeta when defect work begins | On-going |  | TBA
Open | Window winders all buildings | K&S BMS & Metro Locksmiths | A large number of window winders in the complex are weathered and rusted and pose an issue when trying to close and/or open | Inspected and progressed through all buildings in order to ascertain any faulty window winders or WW which needed attention. 13.08.2013 32x window winders throughout the complex were serviced and 7x WW were replaced. | On-going
Open | Apartment 404 balcony deck | K&S BMS | Wooden deck is weathered and expanding after rain making it difficult for resident to open and close sliding balcony door | Inspected and found that the deck is expanding into the balcony slide door making it difficult to open and close. Have engaged a handyman to shave deck in order to open and close door | Completed 9.08.2013
Open | Pebbles throughout common areas | K&S BMS | Some areas around the complex have seen the pebbles stained with dirt and rust | Have asked Syds maintenance to provide a quote to replace stained pebbles around common areas. Quote accepted and new/fresh pebbles placed around common area where required. | Completed 26.08.2013
Open | Common area pavers | K&S BMS | Some common area pavers are becoming uneven and pose as a tripping hazard | Have inspected and found that roots under some pavers are dislodging in some areas and making for uneven surfaces around the complex. Have engaged a tiler for a quote to investigate to repair. Advised that root investigation throughout the complex is warranted/required. | On-going |  | TBA